## 📊 Dashboard
SWUK CENTRAL SUBMISSIONS — PREPAYMENT
Sprint Planning Dashboard · UK Shared Services Digital Solutions · April 2026
| Sprint | Focus | Timeline | Effort | Status | Progress
| Sprint 1 | Core Framework & Provisioning Script | Weeks 1–1.5 | 36 hrs | Active | ████░░░░░░ 40%
| Sprint 2 | Regional Rollout — 23 Plants | Weeks 1.5–3 | Up to 92 hrs | Planned | ░░░░░░░░░░ 0%
| Sprint 3 | QA, Automation & Finance Handover | Week 4 | Included | Planned | ░░░░░░░░░░ 0%
PROJECT PROGRESS
| Total Tasks | Completed | Remaining | % Complete | Sprints | Active Sprint
| 15 | 2 | 13 | 13% | 3 | Sprint 1
ALL TASKS — MASTER LIST
| Task ID | Sprint | Story | Description | Role | Status
| S1-T-001 | Sprint 1 | ST-1.1 | Define and create the "Prepayment Item" Site Content Type and Site Columns. Completed via POC — no rework required. | Frontend | Done
| S1-T-002 ⭐ | Sprint 1 | ST-1.2 | Develop and fully test the PnP PowerShell 1.5.0 provisioning script. Includes end-to-end pilot run against at least one plant before Sprint 2. | Backend | Done
| S1-T-003 | Sprint 1 | ST-1.3 | Provision SharePoint Security Groups for all 23 plants following the [Plant Code] Members convention using the script. | QA | To Do
| S1-T-004 | Sprint 1 | ST-1.4 | Configure base permissions at the site level to allow group discovery while maintaining isolation. | PM | To Do
| S1-T-005 | Sprint 1 | ST-2.1 | Execute PnP script to create Prepayment Request lists for each UK plant (NOC, WEA, SBG, etc.). | Deploy | To Do
| S2-T-001 | Sprint 2 | ST-2.2 | Break permission inheritance and assign unique [Plant Code] Members group permissions on all 23 plant lists via the PnP script. | Frontend | To Do
| S2-T-002 | Sprint 2 | ST-2.3 | Configure "Pending" (Processed=No) and "Processed" (Processed=Yes) views on all plant lists and integrate into Microsoft Teams App Tabs. | Backend | To Do
| S2-T-003 | Sprint 2 | ST-2.4 | Provision Site Pages for each plant using the reusable Plant Page template with SharePoint List webpart filtered to the plant's list. | QA | To Do
| S2-T-004 | Sprint 2 | ST-3.1 | Create the Facilities Master List with columns: SAP Code, Plant Name, List Name, Group ID, GM, Active. Pre-populate all 23 plants. | PM | To Do
| S2-T-005 | Sprint 2 | ST-3.2 | Create the Prepayment Request Master List inheriting all Prepayment Item fields plus Source Plant and Master Processed Date. | Deploy | To Do
| S3-T-001 | Sprint 3 | ST-3.3 | Develop Power Automate Consolidation Flow: reads Facilities Master List, iterates active plants, queries unprocessed items, creates in Master List. New plants auto-included — no flow edits required. | Frontend | To Do
| S3-T-002 | Sprint 3 | ST-3.4 | Implement Sealing logic: break role inheritance on consolidated source items, assign Read to plant group (MembershipGroupId), Full Control to Site Owners (ID 3). Stamp Processed On timestamp. | Backend | To Do
| S3-T-003 | Sprint 3 | ST-4.1 | Functional testing: per-plant isolation. End-to-end consolidation with data from at least 3 plants. Zero data loss or duplication. UAT with Finance Team. | QA | To Do
| S3-T-004 | Sprint 3 | ST-4.2 | Produce Plant Onboarding documentation: step-by-step guide for Finance Team to onboard a new plant independently using PnP script and Facilities Master List. | PM | To Do
| S3-T-005 | Sprint 3 | ST-4.3 | Deliver KT session covering: monthly consolidation trigger, Master List review, plant onboarding process. Finance Team signs off on self-management readiness. | Deploy | To Do

## 🏃 Sprint 1
SPRINT 1 — CORE FRAMEWORK & PROVISIONING SCRIPT
Timeline: Weeks 1–1.5 · Effort: 36 hrs · Status: Active
SPRINT GOAL
Build the core infrastructure foundation with the PnP PowerShell 1.5.0 provisioning script as the priority deliverable. A battle-tested script compresses Sprint 2 from manual per-plant effort into automated batch execution. Priority: (1) Develop & pilot PnP script end-to-end on at least one plant. (2) Harden the Power Automate Consolidation Flow. (3) Create Plant Page template. Capacity note: If sprint completes early, remaining time is redirected to Finance Team SharePoint tasks within GBR-UK-Shared-Services.
USER STORIES
| Story ID | Description |  |  |  | Status
| ST-1.1 | Define and create the "Prepayment Item" Site Content Type and Site Columns. |  |  |  | Done (POC)
| ST-1.2 ⭐ | Develop the PnP PowerShell 1.5.0 script for automated provisioning of security groups and lists. Includes end-to-end pilot run on at least one plant. |  |  |  | Done
| ST-1.3 | Provision SharePoint Security Groups for all 23 plants following the [Plant Code] Members convention. |  |  |  | To Do
| ST-1.4 | Configure base permissions at the site level to allow group discovery while maintaining isolation. |  |  |  | To Do
| ST-2.1 | Execute PnP script to create Prepayment Request lists for each UK plant (NOC, WEA, SBG, etc.). |  |  |  | To Do
TASK BREAKDOWN
| Task ID | Story | Description | Role | Pts | Status
| S1-T-001 | ST-1.1 | Define and create the "Prepayment Item" Site Content Type and Site Columns. Completed via POC — no rework required. | Frontend | 3 | Done
| S1-T-002 ⭐ | ST-1.2 | Develop and fully test the PnP PowerShell 1.5.0 provisioning script. Includes end-to-end pilot run against at least one plant before Sprint 2. | Backend | 5 | Done
| S1-T-003 | ST-1.3 | Provision SharePoint Security Groups for all 23 plants following the [Plant Code] Members convention using the script. | QA | 3 | To Do
| S1-T-004 | ST-1.4 | Configure base permissions at the site level to allow group discovery while maintaining isolation. | PM | 3 | To Do
| S1-T-005 | ST-2.1 | Execute PnP script to create Prepayment Request lists for each UK plant (NOC, WEA, SBG, etc.). | Deploy | 3 | To Do
Sprint Points: 17 total · 8 done · 9 remaining
QA & ACCEPTANCE CRITERIA
| Story | Acceptance Criteria |  |  | Notes
| ST-1.1 | "Prepayment Item" Content Type exists at site level with all required fields. |  |  | Done via POC — no re-testing needed unless fields modified.
| ST-1.2 ⭐ | Script provisions a pilot plant end-to-end: security group created, list created with Content Type, permissions broken and assigned. |  |  | Script must be idempotent — re-runnable without duplicating artefacts.
| ST-1.3 | All 23 [Plant Code] Members groups exist in the site with correct naming. |  |  | Verify via SharePoint Admin Centre.
| ST-1.4 | Site-level permissions allow group discovery. Users can be added without Site Admin rights. |  |  | Test with a non-admin account.
| ST-2.1 | At least one plant list exists with Prepayment Item CT, Pending/Processed views, isolated permissions. |  |  | Full rollout continues in Sprint 2.
RISK REGISTER
| Risk |  |  | Likelihood | Mitigation
| PnP script incompatibility with tenant permissions |  |  | Medium | Test against dev account (s2-gis-mxl1-msflows@smurfitkappa.com) before production run.
| Script run time exceeds window for 23 plants |  |  | Low | Pilot on 1 plant first; batch remaining in Sprint 2.
| Sprint 1 completes early |  |  | Low–Medium | Remaining capacity redirected to Finance Team SharePoint tasks — no idle time.

## 🏃 Sprint 2
SPRINT 2 — REGIONAL ROLLOUT — 23 PLANTS
Timeline: Weeks 1.5–3 · Effort: Up to 92 hrs · Status: Planned
SPRINT GOAL
Provision and secure all 23 Spoke lists using the script validated in Sprint 1. Script automation is expected to reduce actual effort significantly below the 92-hour baseline (23 plants × 4h/plant manual estimate). Configure Teams integration, views, site pages, and master lists.
USER STORIES
| Story ID | Description |  |  |  | Status
| ST-2.2 | Break permission inheritance and assign unique group permissions via automation. |  |  |  | To Do
| ST-2.3 | Configure "Pending" and "Processed" views and integrate lists into Microsoft Teams App Tabs. |  |  |  | To Do
| ST-2.4 | Provision Site Pages for each plant using the reusable Plant Template. |  |  |  | To Do
| ST-3.1 | Create the Plant Master List (Facilities) for system configuration. |  |  |  | To Do
| ST-3.2 | Create the Prepayment Request Master List for central data aggregation. |  |  |  | To Do
TASK BREAKDOWN
| Task ID | Story | Description | Role | Pts | Status
| S2-T-001 | ST-2.2 | Break permission inheritance and assign unique [Plant Code] Members group permissions on all 23 plant lists via the PnP script. | Frontend | 3 | To Do
| S2-T-002 | ST-2.3 | Configure "Pending" (Processed=No) and "Processed" (Processed=Yes) views on all plant lists and integrate into Microsoft Teams App Tabs. | Backend | 3 | To Do
| S2-T-003 | ST-2.4 | Provision Site Pages for each plant using the reusable Plant Page template with SharePoint List webpart filtered to the plant's list. | QA | 3 | To Do
| S2-T-004 | ST-3.1 | Create the Facilities Master List with columns: SAP Code, Plant Name, List Name, Group ID, GM, Active. Pre-populate all 23 plants. | PM | 3 | To Do
| S2-T-005 | ST-3.2 | Create the Prepayment Request Master List inheriting all Prepayment Item fields plus Source Plant and Master Processed Date. | Deploy | 3 | To Do
Sprint Points: 15 total · 0 done · 15 remaining
QA & ACCEPTANCE CRITERIA
| Story | Acceptance Criteria |  |  | Notes
| ST-2.2 | User from Plant A receives "Access Denied" accessing Plant B list. |  |  | Each list has broken inheritance with only its own [Plant Code] Members group assigned Contribute.
| ST-2.3 | "Pending" view shows Processed=No items. "Processed" view shows Processed=Yes items. |  |  | Lists render correctly inside Microsoft Teams App Tab.
| ST-2.4 | Each plant has a dedicated SharePoint page displaying its submission list. |  |  | Accessible via Teams or browser.
| ST-3.1 | Facilities Master List contains all 23 plants with all required fields populated. |  |  | Used as Power Automate configuration source.
| ST-3.2 | Master List exists with all Prepayment Item fields plus Source Plant and Master Processed Date. |  |  | Finance Team has read access; plant users cannot access it.
RISK REGISTER
| Risk |  |  | Likelihood | Mitigation
| Teams App Tab configuration per plant is time-consuming |  |  | Medium | Use bulk configuration approach; template the Teams tab settings.
| Plant Master List data incomplete at sprint start |  |  | Low | Pre-populate during Sprint 1 pilot run.
| Permission script misassigns group to wrong list |  |  | Low | Dry-run script with -WhatIf flag before executing on all 23 plants.

## 🏃 Sprint 3
SPRINT 3 — QA, AUTOMATION & FINANCE HANDOVER
Timeline: Week 4 · Effort: Included · Status: Planned
SPRINT GOAL
Validate the platform end-to-end, complete the Power Automate consolidation engine with sealing logic, and leave the Finance Team fully self-sufficient — able to trigger monthly consolidation, review the Master List, and onboard new plants independently without IT assistance.
USER STORIES
| Story ID | Description |  |  |  | Status
| ST-3.3 | Develop the Power Automate Consolidation Flow to dynamically iterate through the Plant Master List. |  |  |  | To Do
| ST-3.4 | Implement the Sealing logic to set processed items to read-only in source lists. |  |  |  | To Do
| ST-4.1 | Conduct functional testing per plant and end-to-end consolidation testing. |  |  |  | To Do
| ST-4.2 | Produce "Plant Onboarding" documentation for Finance. |  |  |  | To Do
| ST-4.3 | Deliver Knowledge Transfer (KT) session to the Finance Team for self-management. |  |  |  | To Do
TASK BREAKDOWN
| Task ID | Story | Description | Role | Pts | Status
| S3-T-001 | ST-3.3 | Develop Power Automate Consolidation Flow: reads Facilities Master List, iterates active plants, queries unprocessed items, creates in Master List. New plants auto-included — no flow edits required. | Frontend | 3 | To Do
| S3-T-002 | ST-3.4 | Implement Sealing logic: break role inheritance on consolidated source items, assign Read to plant group (MembershipGroupId), Full Control to Site Owners (ID 3). Stamp Processed On timestamp. | Backend | 3 | To Do
| S3-T-003 | ST-4.1 | Functional testing: per-plant isolation. End-to-end consolidation with data from at least 3 plants. Zero data loss or duplication. UAT with Finance Team. | QA | 3 | To Do
| S3-T-004 | ST-4.2 | Produce Plant Onboarding documentation: step-by-step guide for Finance Team to onboard a new plant independently using PnP script and Facilities Master List. | PM | 3 | To Do
| S3-T-005 | ST-4.3 | Deliver KT session covering: monthly consolidation trigger, Master List review, plant onboarding process. Finance Team signs off on self-management readiness. | Deploy | 3 | To Do
Sprint Points: 15 total · 0 done · 15 remaining
QA & ACCEPTANCE CRITERIA
| Story | Acceptance Criteria |  |  | Notes
| ST-3.3 | Flow reads Facilities Master List, queries each active plant for unprocessed items, creates in Master List with correct field mapping. |  |  | New plants added to Facilities Master List auto-included — no flow code changes.
| ST-3.4 | After consolidation: source items read-only for plant group, Processed On timestamp set, submitter cannot amend. |  |  | Test sealing on items from at least 3 plants.
| ST-4.1 | All 23 plant lists tested for isolation. End-to-end consolidation with ≥3 plants. Zero data loss or duplication. |  |  | Finance Team validates Master List data accuracy.
| ST-4.2 | Finance Team onboards a new test plant using only the documentation — without IT assistance. |  |  | Documentation validated during UAT.
| ST-4.3 | Finance Team can independently: trigger consolidation, review Master List, initiate plant onboarding. |  |  | Sign-off obtained from Finance Team lead.
RISK REGISTER
| Risk |  |  | Likelihood | Mitigation
| Power Automate throttling on large runs (23 plants) |  |  | Medium | Use concurrency controls in flow; test with full plant set before UAT.
| Finance Team unavailable for KT session |  |  | Low | Schedule KT early in sprint window; record session for reference.
| Sealing logic breaks item editing for Site Owners |  |  | Low | Verify Full Control assignment to Site Owners group in sealing step.

## ℹ️ Legend
LEGEND & KEY
STATUS COLOURS
Done | Task or story fully completed.
In Progress | Task currently being worked on.
To Do | Task not yet started.
PRIORITY MARKERS
⭐ Priority Task | High-priority item — must complete before downstream tasks can begin.
RISK LIKELIHOOD
Low | Unlikely to occur; manageable if it does.
Medium | Possible; requires monitoring and a mitigation plan.
High | Likely or high impact; needs immediate action.
SERVICE ACCOUNTS
Dev / Test | s2-gis-mxl1-msflows@smurfitkappa.com
Production | S2-GBR-UK-Portal@smurfitwestrock.com